## Overview
CourtSense.app — Master Project Plan
Team / League / Community Management Platform — Beta MVP
Last updated: April 27, 2026
Project Pillars
Pillar | Audience | Status | Live URL
Landing Page | All visitors | Live | courtsense.app
Teams | HS / College beach programs | Existing demo, subhub queued | markmcnees.github.io/leon-beach/demo.html → /teams
Leagues | City / club KOTB-QOTB directors | Live (KOTB), pickup tournament beta, subhub queued | courtsense.app/kotb + /kotb-pickup → /leagues
Community | Recreational + competitive players | Pickup live, RSVP redesign shipped, email worker scaffolded, subhub queued | courtsense.app/kotb-pickup → /community
Status Legend
Done | Shipped and verified
In Progress | Currently being built
Queued | Spec'd, ready to build
Blocked | Waiting on external dependency
Future | Planned but not yet scoped
Sheets in this workbook
1. Overview | This page — project summary, status legend, navigation
2. Landing Page | Root + Teams / Leagues / Community subhubs
3. Pickup App | courtsense.app/kotb-pickup (one-day tournament tool, RSVP system)
4. Ratings System | Glicko-2 ratings spanning league + pickup
5. Invites & RSVP | Pickup event invitations, eligibility, notifications
6. Registration | Public join form with admin approval + TruVolley seed
7. Bugs & Issues | Active bugs found during testing
8. Decisions Log | All UX/architectural decisions made

## Landing Page
Landing Page & Subhubs (courtsense.app)
# | Task | Owner | Status | Priority | Notes | Depends On
ROOT LANDING PAGE (courtsense.app/) — LIVE
1.1 | Build courtsense.app/ landing page (three-column hub) | Mark | Done | P0 | Three pillars: Team / League / Community. White bg, layered floating shadow on cards, color-coded top borders. | —
1.2 | Save CourtSense logo as logo.png at courtsense repo root | Mark | Done | P0 | Sibling of index.html. Page references via <img src='logo.png'>. | 1.1
1.3 | Verify deploy at courtsense.app, mobile responsive at 375/414/768/1280px | Mark | Done | P0 | Cards stay side-by-side at all sizes via clamp() sizing. | 1.1, 1.2
1.4 | League card text updated to 'Run a city or club league or one-day tournament' | Claude | Done | P1 | Final wording confirmed. | 1.1
1.5 | Add favicon set (16, 32, 192, 512 + apple-touch) | Mark | Queued | P1 | Use the CourtSense logo at multiple sizes. | 1.2
1.6 | Add Open Graph + Twitter Card meta tags for social sharing previews | Claude Code | Queued | P1 | og:title, og:description, og:image (1200x630 hero card), Twitter summary_large_image. | 1.2
1.7 | Update column buttons to point at subhubs once they ship | Mark | Queued | P2 | Team → /teams. League → /leagues. Community → /community. One-line href change per card. | 2.1, 3.1, 4.1
TEAMS SUBHUB (courtsense.app/teams)
2.1 | Build /teams subhub: hero, problem/solution sections, demo CTA, pricing, lead form | Claude Code | Queued | P1 | CourtSense-branded sales funnel for HS/college coaches. Replaces existing Sand Sharks demo as primary funnel. | 1.3
2.2 | Port Sand Sharks demo to /teams/demo with CourtSense branding | Claude Code | Queued | P2 | Existing demo at markmcnees.github.io/leon-beach/demo.html. Rebrand colors, fonts, copy. Add 'Back to Teams' header link. | 2.1
2.3 | Lead capture form with intake + admin notification email | Claude Code | Queued | P2 | Fields: name, school, role, email, phone, roster size, message. Stores at tally_kotb_pickup/leads/teams/{leadId}/. Queues admin email. | 2.1
2.4 | Update home page Team CTA from /demo.html to /teams | Mark | Queued | P2 | Wait until /teams ships before flipping the link. | 2.1
LEAGUES SUBHUB (courtsense.app/leagues)
3.1 | Build /leagues subhub: hero, geo search, active leagues list, start-your-own CTA | Claude Code | Queued | P1 | Decision = option 3 (geo search). Empty-state of geo search becomes conversion moment ('Be the first to start one'). | 1.3
3.2 | Geolocation/zip code search with haversine distance calc | Claude Code | Queued | P1 | Browser geolocation API + Nominatim/OSM for zip→lat/lng. Client-side, no backend. 'Near you' = within 100 miles. | 3.1
3.3 | Active Leagues list (currently just City of Tallahassee KOTB) | Claude Code | Queued | P1 | Read live config from league app. Show season status, week N of M, # active players. Card links to /kotb. | 3.1
3.4 | Build /leagues/start intake form for prospective league directors | Claude Code | Queued | P2 | Fields: name, email, city, type (curious/ready/switching), expected size, format, message. Stores at tally_kotb_pickup/leads/leagues/. | 3.1
3.5 | Update home page League CTA from /kotb to /leagues | Mark | Queued | P2 | Wait until /leagues ships. | 3.1
COMMUNITY SUBHUB (courtsense.app/community)
4.1 | Build /community subhub with four equal cards in 2x2 grid | Claude Code | Queued | P1 | Cards: Find a Game / Find a Tournament Partner / Find a Training Partner / Register. All teal-accented. Build community-first per build order. | 1.3
4.2 | Find a Game card → /kotb-pickup (existing) | Claude Code | Queued | P1 | Status: Live. Routes to existing pickup app event list. | 4.1
4.3 | Find a Tournament Partner card → /community/partners (placeholder + waitlist) | Claude Code | Queued | P2 | Status: Coming Soon. 'Notify Me' modal collects email, optional skill range, optional city. Stores at tally_kotb_pickup/waitlist/partners/. | 4.1
4.4 | Find a Training Partner card → /community/training (placeholder + waitlist) | Claude Code | Queued | P2 | Status: Coming Soon. Same waitlist modal. Stores at tally_kotb_pickup/waitlist/training/. | 4.1
4.5 | Register card → /kotb-pickup/join (existing) | Claude Code | Queued | P1 | Status: Live. Routes to existing public registration form. | —
4.6 | Update home page Community CTA from /kotb-pickup to /community | Mark | Queued | P2 | Wait until /community ships. | 4.1
4.7 | Build out Find a Tournament Partner feature (post-MVP) | Claude Code | Future | P3 | Match by skill range, tournament name/date, contact preference. Scope when waitlist signal warrants build. | 4.3
4.8 | Build out Find a Training Partner feature (post-MVP) | Claude Code | Future | P3 | Match by skill range, schedule availability, location. Scope when waitlist signal warrants build. | 4.4
SHARED DESIGN SYSTEM
5.1 | Lock shared color palette across all subhubs | Mark | Done | P1 | navy / navy-deep / gold / teal / sand / white / ink / ink-soft. Same as root index.html. | 1.1
5.2 | Lock shared typography (Bebas Neue + Barlow) | Mark | Done | P1 | Same Google Fonts loader. Headings Bebas, body Barlow 400/500/600. | 1.1
5.3 | Sticky 'Back to CourtSense' header on all subhub pages | Claude Code | Queued | P1 | Routes back to /. Same navy text. | 2.1, 3.1, 4.1
5.4 | Shared footer (Built in Tallahassee · contact email) | Claude Code | Queued | P1 | Same as home page. Single footer component reused across subhubs. | 2.1, 3.1, 4.1
5.5 | Floating shadow card style: 0 10px 30px / 0 4px 8px (default), grow on hover | Mark | Done | P1 | Two-layer shadow technique. Already locked in root index.html. | 1.1

## Pickup App
Pickup App (courtsense.app/kotb-pickup)
# | Task | Owner | Status | Priority | Notes | Depends On
CORE PICKUP APP
P.1 | Pickup app deployed at /kotb-pickup/index.html (folder-with-index) | Claude Code | Done | P0 | Live and routing correctly. CNAME serves courtsense.app from courtsense repo. | —
P.2 | Setup screen: event meta + roster builder + Generate Sets | Claude Code | Done | P0 | Default 6 games per player, editable. Quick-select from Kings + Queens + pickup history. | P.1
P.3 | Mid-event drop player → regen all unplayed rounds from scratch | Claude Code | Done | P0 | Active round finishes as-is. Regen kicks in next round. | P.2
P.4 | Mid-event late add → pro-rated games count | Claude Code | Done | P0 | Half rounds done = half games for late add. | P.2
P.5 | End/Extend Event flow with Are-you-sure confirmation | Claude Code | Done | P0 | End anytime including mid-round (rain, etc). Per-player extend counts. | P.2
P.6 | Archive viewer with full standings + tap-for-partner-history modal | Claude Code | Done | P0 | All past events viewable. Aggregated across league + pickup. | P.2
P.7 | Eligibility refactor: separate eligibility from notification reach | Claude Code | Done | P0 | computeEligible now reads union of all known players (kings + queens + ratings + profiles). Only blocked filter applies. Notification preferences only filter at SEND time. | P.2
P.8 | Eligibility summary text honest about source ('X players from league + pickup rosters') | Claude Code | Queued | P1 | Update label so host sees pool reflects whole community. | P.7
P.9 | Inactive league players skipped from auto-eligibility | Claude Code | Done | P1 | Honor the deliberate admin signal. Host can override via include list per-event. | P.7
RSVP FLOW REDESIGN (in progress after dogfood test)
R.1 | Bug 1: Date display off by one day | Claude Code | Done | P0 | Shipped in commit 322a41d (Apr 26). _userEditedTitle flag at index.html:2155, auto-update on date change at line 2166. | —
R.2 | Bug 2: Rename 'Pick your name to RSVP' → 'RSVP to this Event' | Claude Code | Done | P0 | Shipped in commit 322a41d. rsvpFlow() at line 2551, button rename at line 2462. | —
R.3 | Bug 3: 'Add as new player' button rename based on context | Claude Code | Done | P0 | Shipped in commit 322a41d. addLabel: 'RSVP me in' plumbed through Identity.openPicker at line 2556. | —
R.4 | Bug 4: Skip profile modal in RSVP path | Claude Code | Done | P0 | Shipped in commit 322a41d. emailPromptDismissed flag (lines 2566, 2578, 2588). Profile modal removed from RSVP path. | —
R.5 | Strip v3.x debug machinery (overlay obs, hit-test, PROBE, ptrdown loggers) | Claude Code | Done | P1 | Shipped in commit 322a41d alongside R.1-R.4. Mark dogfooded after the fact and confirmed working (R.6). | R.1, R.2, R.3, R.4
R.6 | Final dogfood test: existing RSVP / new user RSVP / new user with skip / date display | Mark | Done | P0 | Mark confirmed pickup app working post-commit (Apr 27). RSVP flow validated in production. | R.5
R.7 | Decision: instant RSVP on name tap, no confirm step | Mark | Done | P1 | Drop Out is the recovery path. Friction cost > rare-misclick cost. | R.4
R.8 | Decision: post-first-RSVP email prompt only, never before, dismissible permanent | Mark | Done | P1 | User can RSVP and leave without ever seeing notification settings. | R.4

## Ratings
Glicko-2 Ratings System (cross-app)
# | Task | Owner | Status | Priority | Notes | Depends On
RATINGS CORE
RT.1 | Glicko-2 algorithm with logarithmic margin-of-victory weighting | Claude Code | Done | P0 | Standard formula: multiplier = ln(margin+1) * (2.2 / ((winnerR-loserR)*0.001+2.2)) | —
RT.2 | Ratings storage at tally_kotb_pickup/ratings/{playerName}/ | Claude Code | Done | P0 | rating, rd, volatility, gamesPlayed, peakRating, peakRatingDate, lastUpdated, history/ | —
RT.3 | Cross-app rating writes (league Kings + Queens + pickup all update same record) | Claude Code | Done | P0 | League app writes to tally_kotb_pickup/ratings on every saveResult. Pickup app same. | RT.1
RT.4 | Historical seed migration (replay all past results from all sources) | Claude Code | Done | P0 | Reads tally_kotb/kings/results, queens/results, archives, pickup archives. Sorts chronologically. Seeds at 1500/350/0.06. | RT.2
RT.5 | Skip sub games in rating updates (match calcStats subSlots logic) | Claude Code | Done | P0 | Subs flagged in result.subSlots[] do not get rating updates. | RT.1
RT.6 | Ratings tab in both apps (sortable table + header stats + How Ratings Work info) | Claude Code | Done | P0 | League Kings + Queens + pickup all show same Ratings tab. Default sort by rating desc. | RT.1
RT.7 | Rating breakdown modal (replaces partner history modal) | Claude Code | Done | P0 | Tap player → header (rating, RD, W/L) + recent games + chart + best/worst + partner breakdown. | RT.1
RT.8 | Audit migration covers ALL data sources (was only showing 4 players) | Claude Code | Done | P0 | Bug fixed. Now pulls league Kings/Queens/archives/pickup. Seeds full community in one pass. | RT.4
ADMIN RATINGS MANAGEMENT
AR.1 | Manage Ratings admin tool (PIN-gated, /admin-ratings.html) | Claude Code | Done | P1 | Edit name, delete player, merge players. Strict isolation: only writes to tally_kotb_pickup/ratings. | RT.6
AR.2 | Edit name → renames key + updates history references | Claude Code | Done | P1 | Does NOT touch source data in tally_kotb/kings/queens/. | AR.1
AR.3 | Merge players → combine history, recompute from 1500/350/0.06 | Claude Code | Done | P1 | For 'Mark' vs 'Mark McNees' duplicates. | AR.1
AR.4 | Re-creation gotcha warning surfaced in admin tool UI | Claude Code | Done | P1 | Rename here, but source data still has old name → re-created on next sync. | AR.1

## Invites & RSVP
Pickup Event Invites & RSVP System
# | Task | Owner | Status | Priority | Notes | Depends On
EVENT CREATION & ELIGIBILITY
I.1 | Create Event form (name, date, time, location, slots, deadline, recurring) | Claude Code | Done | P0 | Recurring weekly/biweekly. Generates N events at once. | —
I.2 | Eligibility resolver (open / ratingMin / ratingRange / group + include/exclude) | Claude Code | Done | P0 | Refactored to read full union of player sources. Fixed in P.7. | I.1
I.3 | Saved groups (named reusable invitation lists) | Claude Code | Done | P1 | tally_kotb_pickup/groups/{groupId}/. Anyone can create. | —
I.4 | Eligibility summary text reflects accurate count + sources | Claude Code | Queued | P1 | After fix: '32 players currently eligible from league + pickup rosters'. | I.2
RSVP FLOW
I.5 | First-come-first-served opt-in with auto waitlist promotion | Claude Code | Done | P0 | Slots fill in tap order. Drop-out promotes next waitlist person. | I.1
I.6 | RSVP deadline enforcement (no opt-ins after, waitlist promotions still allowed until start) | Claude Code | Done | P0 | Default deadline 2 hours before event start. | I.1
I.7 | Magic link tokens for RSVP via email (opt-in / decline / drop) | Claude Code | Done | P0 | Single-use for opt-in/decline. Drop tokens valid until event ends. | —
I.8 | Add to Calendar (.ics file) on confirmation page + email | Claude Code | Done | P1 | Client-side ICS generation. Works with Google/Apple/Outlook. | I.5
NOTIFICATIONS (Phase 5: Cloudflare Worker + Resend)
N.1 | Email queue at tally_kotb_pickup/email_queue/{id} with status: queued¦sent | Claude Code | Done | P0 | Three types: admin_new_registration, welcome, decline. Adding invite + reminder + waitlist_promo in Phase 5. | —
N.2 | Cloudflare Worker reads email_queue, dispatches via Resend | Claude Code | In Progress | P0 | Worker scaffolded at courtsense-email-worker repo (TS, wrangler v3, Firebase REST via service account, Resend dispatch). Awaiting wrangler kv namespace, RESEND_API_KEY secret, FIREBASE_SERVICE_ACCOUNT_JSON secret, and deploy. | N.1
N.3 | Worker cron trigger (hourly) for 24-hour reminders | Claude Code | In Progress | P0 | Cron handler scaffolded (scanForReminders walks invites/*, queues for 23-25h window, sets reminderSent flag). Lives in same worker repo. Activates on deploy. | N.2
N.4 | Email templates: invite, reminder, waitlist promo, admin notification, welcome, decline | Claude Code | Done | P0 | Full spec committed at courtsense/docs/email-templates.md. Three templates (invite, reminder, waitlist promo) with subjects, preheaders, HTML, plain-text fallbacks, merge field reference, implementation notes, testing checklist. | N.2
N.5 | Rate limit Worker endpoints (5 invite-creates per host per minute) | Claude Code | In Progress | P1 | Defensive floor implemented in worker via KV per-host throttle (5 invites/host/min default). App-side enforcement still queued. | N.2
N.6 | In-app banner on every screen of both apps when player has open invites | Claude Code | Done | P0 | Yellow/gold banner. Tapping routes to event detail in pickup app. | I.5
N.7 | Scaffold courtsense-email-worker repo (TypeScript, wrangler, Firebase REST, Resend) | Claude Code | Done | P0 | Separate repo from leon-beach-ai per D.35. Includes templates/ dir with invite, reminder, waitlist builders. Type-safe ctx hydration. tsc --noEmit passes clean. | N.4
N.8 | Wire magic-link tokens into worker dispatch (currently plain deep links per D.36) | Claude Code | Queued | P1 | Mint single-use tokens at queue.ts before dispatch, write to tally_kotb_pickup/rsvp_tokens/{token} with expiry, validate on app side. Defer until forwarding-as-attack becomes a real concern. | N.2
N.9 | Confirm admin_new_registration dispatch path (worker currently marks skipped_unsupported) | Mark | Queued | P1 | Verify where this email type is currently sent from before worker goes live. If supposed to flow through queue, worker needs handler. If separate path, leave as is. | N.2

## Registration
Public Registration with Admin Approval
# | Task | Owner | Status | Priority | Notes | Depends On
PUBLIC REGISTRATION FORM
RG.1 | Public form at courtsense.app/kotb-pickup/join | Claude Code | Done | P0 | Name, email, phone, TruVolley name, referrer, notification opt-in. | —
RG.2 | Submit creates pending_registrations + queues admin notification email | Claude Code | Done | P0 | Status: pending. User confirmation: 'You'll get an email when approved.' | RG.1
RG.3 | Spam protection: rate limit 5/IP/hour + honeypot field | Claude Code | Queued | P1 | Need to verify wired correctly. Test plan step 7 was incomplete. | RG.1
ADMIN APPROVAL FLOW
RG.4 | Admin Pending Registrations screen at /admin-players.html (PIN-gated) | Claude Code | Done | P0 | Lives at root of courtsense repo. Shows queue with Look up on TruVolley/VolleyballLife buttons. | —
RG.5 | Starting Rating + RD override fields with TruVolley→Glicko-2 mapping | Claude Code | Done | P0 | Default 1500/350. Mapping table shown on screen for admin convenience. | RG.4
RG.6 | Approve creates player + rating record, queues welcome email | Claude Code | Done | P0 | Player at tally_kotb_pickup/players/{normalizedName}. Rating at .../ratings/{normalizedName}. | RG.4
RG.7 | Reject flips status, optional decline email gated on admin checkbox | Claude Code | Done | P0 | Reason field optional. | RG.4
RG.8 | Test fresh end-to-end (Test McTesty rejected, Test McTesty2 approved) | Mark | In Progress | P0 | Original test plan steps 3-8. | RG.6, RG.7

## Bugs & Issues
Active Bugs & Issues
# | Bug | Severity | Status | Surface | Notes / Fix | Found By
B.1 | Date display off by one day ('Pickup, Apr 26' but actual date Mon Apr 27) | P0 | Done | Pickup app event card + listing | FIXED in commit 322a41d. _userEditedTitle flag prevents auto-title from clobbering user edits while still updating on pure date changes. | Mark dogfood
B.2 | 'Pick your name to RSVP' button promises action it doesn't deliver | P0 | Done | Pickup app RSVP path | FIXED in commit 322a41d. New rsvpFlow() chains picker → identity → optInInvite → optional email prompt. | Mark dogfood
B.3 | 'Add as new player' reinforces wrong mental model | P0 | Done | Pickup app identity picker | FIXED in commit 322a41d. addLabel option on Identity.openPicker. Default 'Add yourself', RSVP context 'RSVP me in'. | Mark dogfood
B.4 | Profile setup modal mid-RSVP creates friction (4 screens to RSVP) | P0 | Done | Pickup app first-time RSVP | FIXED in commit 322a41d. Profile modal removed from RSVP path. Post-RSVP dismissible 'Want email reminders?' card with permanent skip flag. | Mark dogfood
B.5 | 'Open to all' eligibility shows only 7 players (filtering by notification status) | P0 | Done | Pickup event creation | FIXED: computeEligible was using profilesActiveNow which filters by notifications. Now reads union of all known players, only blocked filter applies. | Mark dogfood
B.6 | Identity auto-resolves to first player in incognito (silently picks bruna_olivera) | P2 | Future | Pickup app first load | Should default to no identity or prompt to pick rather than silently selecting a real player. Less urgent now that we know about it. | Mark dogfood
B.7 | FALSE ALARM: Opt In button 'broken' (debug v3.2-v3.5 hunt) | Closed | Done | Pickup app | Was Mark skipping the actual Opt In tap, assuming Save Profile = RSVP. Surfaced real UX bugs B.2-B.4. Useful false alarm. | Mark dogfood

## Decisions Log
Architectural & UX Decisions Log
# | Topic | Decision | Rationale | Date / Source
D.1 | Landing page architecture | Three-column hub at courtsense.app/ root. Each column links to a dedicated subhub. | Lets visitors self-select their path. Avoids forcing one audience through irrelevant copy. | Convo Q1-Q5
D.2 | Hero treatment | Logo + minimal copy. The logo IS the wordmark + tagline + icon set. | Don't duplicate what the logo already says. Let it do the work. | Convo follow
D.3 | Background | White, not sand. Layered floating shadow on cards. | Cleaner. Lets colored top borders pop. Cards feel lifted. | User feedback
D.4 | Cards always side-by-side (no mobile stacking) | Fluid clamp() sizing. Cards scale down rather than stacking. | Visual continuity. User explicitly requested side-by-side layout at all sizes. | User feedback
D.5 | Beta framing | All three columns labeled Beta. CTA copy: Manage Team / Run a League / Get Connected. | Honest framing attracts engaged early users. Specific verbs > generic Enter. | Convo Q3-Q4
D.6 | Teams subhub | CourtSense-branded sales funnel at /teams. Absorb existing Sand Sharks demo at /teams/demo. | Full brand consolidation. More work but better long-term. | Convo Q7
D.7 | Leagues subhub structure | Hero + geo search + active leagues list + start-your-own intake. | Geo search future-proofs. Empty state ('Be the first') is the conversion moment. | Convo Q8
D.8 | Community subhub structure | Four equal cards (2x2 grid): Find a Game / Tournament Partner / Training Partner / Register. | Visual continuity with home page. Symmetric. | Convo Q9
D.9 | Coming-Soon features get a waitlist | 'Notify Me' modal collects emails for tournament/training partner features. | Validates demand before building. Mark can email waitlist when feature ships. | Subhub brief
D.10 | Pickup app games default | 6 games per player as global default, editable at setup. Locked after Generate Sets. | Sensible default for half-day pickups. Mid-event change only via End/Extend. | Pickup brief
D.11 | Mid-event drop-out behavior | Regenerate ALL unplayed rounds from scratch using only remaining players. | Cleanest fairness math. Active round finishes undisturbed. | Pickup brief Q3
D.12 | Late-add games count | Pro-rated based on rounds remaining. Half done = half games. | Keeps event ending on time without manual math. | Pickup brief Q4
D.13 | End/Extend always available | Manual button always visible. End anytime including mid-round (rain, lightning). | Real game-day flexibility. Required Are-you-sure confirmation for End. | Pickup brief Q7
D.14 | Rating algorithm | Glicko-2 with logarithmic margin-of-victory weighting. | Standard modern Elo derivative. Matches FIFA/chess.com convention. | Ratings brief Q1-Q4
D.15 | Rating data scope | League Kings + Queens + pickup all write to one shared rating record at tally_kotb_pickup/ratings. | Single rating per player across all play. League app must read+write only ratings node, never league source data. | Ratings brief Q1
D.16 | Historical seed | One-time replay of all past results, sorted chronologically, applied game-by-game. | Day-one ratings reflect real history. Better UX than waiting weeks for ratings to converge. | Ratings brief Q2
D.17 | League vs pickup weighting | Equal weight. All games count the same. | Simpler logic, more data points. | Ratings brief Q3
D.18 | Default standings view | Stays W/L based in league app (unchanged). Ratings tab is parallel view. | Don't disrupt familiar standings. Ratings is added value. | Ratings brief
D.19 | AI scheduler does NOT use ratings | Partner variety only. No team balancing. | Keeps simple rotation logic. Balancing is future feature, not MVP. | Ratings brief Q1
D.20 | Notification channels | In-app banner + email. No SMS, no web push. | Email is reliable across all devices. Banner reaches engaged users. Free at scale. | Invites brief Q1
D.21 | Email source | Self-service via player profile. Admin block tool for bad actors. | Lower friction than admin entering everyone. Block flag prevents email re-add. | Invites brief Q2 + follow
D.22 | Eligibility model | Layered: base mode (open/ratingMin/ratingRange/group) + include list + exclude list. Saved groups reusable. | Covers all use cases without complexity tax for simple cases. | Invites brief Q4
D.23 | RSVP model | First-come-first-served with auto waitlist promotion. | Simplest, fairest. Host doesn't need to curate every event. | Invites brief Q5
D.24 | Notification triggers | Event created + 24-hour reminder + waitlist promotion. No other moments. | Standard pickup-league pattern. Avoids notification fatigue. | Invites brief Q7
D.25 | App placement of invites | Banner in both apps. RSVP/event detail screens only in pickup app. | Maximum reach for new invites without bloating the league app's UI. | Invites brief Q8
D.26 | Calendar integration | ICS file download. No Google Calendar OAuth integration. | Works with all calendar apps. No tokens, API keys, or partnership-required. | User Q
D.27 | External rating source | TruVolley name (rating, confidence, history all visible on volleyballlife.com). | Better fit than AVP points. Glicko-derivative, individual ratings, partner-switch aware. | Convo + research
D.28 | TruVolley lookup method | Manual via 'Look up on TruVolley' button on admin approval screen. No API integration. | No public TruVolley API exists. Manual sustainable for low-volume admin approvals. | Web research
D.29 | Glicko-2 starting rating | 1500/350/0.06 default. Admin can override at approval time using TruVolley→Glicko mapping. | Matches algorithm convention. Override field gives admin precision when external data exists. | Ratings brief
D.30 | Inactive league players in pickup eligibility | Skip by default. Host can override with include list per-event. | 'Inactive' is a deliberate admin signal. Auto-including undermines it. | Bug B.5 fix
D.31 | Instant RSVP on name tap (no confirm) | Ship without confirm. Drop Out is the recovery path. | Friction cost of confirm-every-RSVP > rare-misclick cost. | Bug B.4 redesign
D.32 | Email prompt timing | Show ONLY after first successful RSVP for new users. Never before. Dismissible permanent flag. | User can RSVP and leave without ever seeing notification settings. | Bug B.4 redesign
D.33 | Eligibility separated from notification reach | Eligibility = who CAN RSVP. Notification reach = who gets notified. Two separate filters at two separate times. | Conflating the two caused B.5 (only 7 eligible). Clean separation prevents recurrence. | Bug B.5 architecture fix
D.34 | Subhub build order | Community first (uses 100% existing destinations). Leagues second. Teams last (biggest scope). | Minimize risk, ship value early. Coming-Soon waitlist is a tiny modal not a new page. | Subhub brief
D.35 | Email worker as separate repo | New courtsense-email-worker repo, separate from leon-beach-ai. TypeScript + wrangler v3 + Firebase REST + Resend. | Email is its own concern with its own scaling profile (cron + waitlist promos throughout day vs bursty AI calls on game night). Cleaner secrets boundary. Adding cron to leon-beach-ai would change its character. | Worker scaffold session
D.36 | Magic-link tokens deferred for worker v1 | Worker dispatches plain deep links (?invite=...&action=...&u=...) for v1. Token-mint step deferred to N.8. | Tallahassee community is small enough that forwarding-as-attack isn't a real threat day one. Worker shipping is more valuable than perfect token security. Hardens later when scale warrants. | Worker scaffold session